## Slide 1
Pre-Planning: Align to Strategic Healthy Governance Operations/Strategic Planning Cycle
Fiscal Year
Aug
Sept
Oct
Nov
Dec
Jan
Feb
Mar
April
June
May
Implement
Board Approve
Check-ins at Staff Meetings, Board Meetings & Committee Meetings
Q3 Comprehensive Review with Board
Q4 Comprehensive Review with Board
July
Pre-Planning
SWOT
Data Analytics
Creation
Goals & SMARTIE Objectives
Implement
Action Plan
Monitor
Q1 Comprehensive Review with Board
Prioritization
Evaluate Performance
Review Annual Progress& Continue Cycle
Q2 Comprehensive Review with Board
Q1
Q2
Q3
Q4
Align to Budget
Notes: We just zoomed out on the essential, leading, and compliance best practices of governance – which included strategic planning as an essential best practice. Then we looked at how some of those governance operations fit into an annual governance timeline – which included strategic planning….Lastly, let’s zoom in on ONLY the Strategic Planning Cycle.
This is an example, and it is aligned to a fiscal year with Q1 starting in July. You could certainly adjust this cycle for a calendar year council.
This chart zooms into each of the five steps: pre-planning, creation, implementation, monitoring and evaluation.
Utilizing what we have learned from the five step process, if you are following a fiscal year strategic planning cycle, your Pre-Planning cycle could begin in January with:
Data Analytics ENTER which would inform your SWOT activity in Feb.
Following the SWOT activity, you would begin to create the plan by prioritizing all of the great ideas that came out of the SWOT activity. Once they were narrowed down, you create your Goals and measurable objectives. Around this time, you will want to ensure that your plan is achievable by ensuring your budget can support it.
Now that you have your goals and objectives, and your budget is aligned to your work, it is time to create the action plan. Be sure to use the Action Plan Template included in the Strategic Planning Five Step Guide to support the framework for what the activity is, who will do it, when it needs to be done by, and how it will be measured.
Once the Action Plan is completed, it’s time to implement, implement, implement! This is ongoing! We are always implementing.
Since we are always implementing, there is always something to monitor and evaluate! In Part 1 of this webinar series, we reviewed the Five Step Process visual – step 5 is monitor and the first bullet point was “Set Check Points”. This cycle reinforces your check points and provides guidance on when they can occur. A best practice would be to have check points at monthly staff meetings, board meetings, and committee meetings. While board and committee meetings can likely be monthly updates, staff check points could be as often as weekly at staff meetings! Just set aside 5-10 minutes weekly to discuss progress to any program-related goal. Another best practice, in addition to monthly check points with the board, is a quarterly comprehensive review.
Just as a quarterly comprehensive review can be beneficial, so can an annual comprehensive evaluation. An annual evaluation (post implementation) would allow you to evaluate the full year, celebrate, adjust, and continue the cycle.

## Slide 2
Pre-Planning: Align to Strategic Healthy Governance Operations/Strategic Planning Cycle
Calendar Year
Aug
Sept
Oct
Nov
Dec
Jan
Feb
Mar
April
June
May
Implement
Board Approve
Check-ins at Staff Meetings, Board Meetings & Committee Meetings
Q3 Comprehensive Review with Board
Q4 Comprehensive Review with Board
July
Pre-Planning
SWOT
Data Analytics
Creation
Goals & SMARTIE Objectives
Implement
Action Plan
Monitor
Q1 Comprehensive Review with Board
Prioritization
Evaluate Performance
Review Annual Progress& Continue Cycle
Q2 Comprehensive Review with Board
Q1
Q2
Q3
Q4
Align to Budget
Notes: We just zoomed out on the essential, leading, and compliance best practices of governance – which included strategic planning as an essential best practice. Then we looked at how some of those governance operations fit into an annual governance timeline – which included strategic planning….Lastly, let’s zoom in on ONLY the Strategic Planning Cycle.
This is an example, and it is aligned to a fiscal year with Q1 starting in July. You could certainly adjust this cycle for a calendar year council.
This chart zooms into each of the five steps: pre-planning, creation, implementation, monitoring and evaluation.
Utilizing what we have learned from the five step process, if you are following a fiscal year strategic planning cycle, your Pre-Planning cycle could begin in January with:
Data Analytics ENTER which would inform your SWOT activity in Feb.
Following the SWOT activity, you would begin to create the plan by prioritizing all of the great ideas that came out of the SWOT activity. Once they were narrowed down, you create your Goals and measurable objectives. Around this time, you will want to ensure that your plan is achievable by ensuring your budget can support it.
Now that you have your goals and objectives, and your budget is aligned to your work, it is time to create the action plan. Be sure to use the Action Plan Template included in the Strategic Planning Five Step Guide to support the framework for what the activity is, who will do it, when it needs to be done by, and how it will be measured.
Once the Action Plan is completed, it’s time to implement, implement, implement! This is ongoing! We are always implementing.
Since we are always implementing, there is always something to monitor and evaluate! In Part 1 of this webinar series, we reviewed the Five Step Process visual – step 5 is monitor and the first bullet point was “Set Check Points”. This cycle reinforces your check points and provides guidance on when they can occur. A best practice would be to have check points at monthly staff meetings, board meetings, and committee meetings. While board and committee meetings can likely be monthly updates, staff check points could be as often as weekly at staff meetings! Just set aside 5-10 minutes weekly to discuss progress to any program-related goal. Another best practice, in addition to monthly check points with the board, is a quarterly comprehensive review.
Just as a quarterly comprehensive review can be beneficial, so can an annual comprehensive evaluation. An annual evaluation (post implementation) would allow you to evaluate the full year, celebrate, adjust, and continue the cycle.